## Current Iteration
|  | Sprint Number: |  |  |  | 1
|  | Expected Total effort: |  |  |  | 17
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Make wiring diagram | 5 | [20 empty] | 2 | 60% | bar: Days (Points Completed) 1 to Days (Points Completed) 3
Write code | 5 | [20 empty] | 1 | 80% | bar: Days (Points Completed) 1 to Days (Points Completed) 4
Assemble device | 5 | [20 empty] | 3 | 40% | bar: Days (Points Completed) 1 to Days (Points Completed) 2
Test project | 2 | [20 empty] | 2 | 0%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Effort Remaining | 17 | 14 | 11 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 52.94%
Ideal Trend | 17 | 15.3 | 13.6 | 11.9 | 10.2 | 8.5 | 6.8 | 5.1 | 3.4 | 1.7 | 3.1086e-15 | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days