## Current Iteration
|  | Sprint Number: |  |  |  | 1
|  | Expected Total effort: |  |  |  | 29
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Research/brainstorm overall look of the device | 9 | Days (Points Completed) 2: 1; Days (Points Completed) 5: 2; Days (Points Completed) 7: 1; Days (Points Completed) 8: 1; Days (Points Completed) 10: 1; Days (Points Completed) 11: 3 | 0 | 100%
Research possible microcontrollers | 7 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 3 to Days (Points Completed) 7; Days (Points Completed) 9; Days (Points Completed) 14
What language will we code in | 1 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 5
Research other hardware components we might need | 6 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 2; Days (Points Completed) 4; Days (Points Completed) 7; Days (Points Completed) 9 to Days (Points Completed) 10; Days (Points Completed) 12
Research hardware requirements of the device | 6 | Days (Points Completed) 1: 1; Days (Points Completed) 3: 2; Days (Points Completed) 6: 1; Days (Points Completed) 7: 1; Days (Points Completed) 8: 1 | 0 | 100%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Effort Remaining | 29 | 28 | 26 | 23 | 21 | 17 | 15 | 11 | 9 | 7 | 5 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100%
Ideal Trend | 29 | 26.1 | 23.2 | 20.3 | 17.4 | 14.5 | 11.6 | 8.7 | 5.8 | 2.9 | 4.4409e-15 | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days