## Current Iteration
|  | Sprint Number: |  |  |  | 1
|  | Expected Total effort: |  |  |  | 27
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Order components and assemble | 10 | [20 empty] | 10 | 0%
Test each component (Display, buttons, alarm etc) | 8 | [20 empty] | 8 | 0%
Start with simple code | 3 | [20 empty] | 3 | 0%
Continue Research for the project | 6 | [20 empty] | 6 | 0%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Effort Remaining | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 0%
Ideal Trend | 27 | 24.3 | 21.6 | 18.9 | 16.2 | 13.5 | 10.8 | 8.1 | 5.4 | 2.7 | 4.4409e-15 | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days